## Sheet1
BIRTHDAY FUNCTION PROJECT PLAN
TASKS | ASSIGNED TO | START DATE | FINISH DATE | STATUS
Requirement documentation | Tumi (female) and Tshepiso | 18/09/2013 | 27/09/2013 | completed
Login function for android | Asheen | 18/09/2013 | 27/09/2013 | in progress
intergrating web app with database | Bandile | 18/09/2013 | 27/09/2013 | in progress
Testing web app | Tumi (female) | 25/09/2013 | 2013-01-10 | in progress
Implementing push notification | Snowy | 18/09/2013 | 2013-02-10 | in progress
retreving data from database for the push notification | Tumi (male) | 18/09/2013 | 2013-02-10 | in progress
Storing push notification on mobile device | Asheen and Bandile | 25/09/2013 | 2013-02-10 | in progress
Testing mobile app | Tshepiso | 2013-02-10 | 2013-04-10 | in progress